## 1st
ANNEX B
Technical Education and Skills Development Authority
Cordillera Administrative Region
Procurement Monitoring Report as of June 2018
Code (UACS/PAP) | Procurement Program/Project | PMO/ End-User | Mode of Procurement | Actual Procurement Activity | [11 empty] | Source of Funds | ABC (PhP) |  |  | Contract Cost (PhP) |  |  | List of Invited Observers | Date of Receipt of Invitation | [5 empty] | Remarks (Explaining changes from the APP)
|  |  |  | Pre-Proc Conference | Ads/Post of IB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Notice of Award | Contract Signing | Notice to Proceed | Delivery/ Completion | Inspection & Acceptance |  | Total | MOOE | CO | Total | MOOE | CO |  | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Delivery/ Completion/ Acceptance (If applicable)
COMPLETED PROCUREMENT ACTIVITIES
[17 empty] | 0 |  |  | 0
| Provision of Security Services | [15 empty] | 0
| Requirement for TESDA-CAR | RO | Public Bidding | 2017-10-26 | 2017-10-29 | 2017-11-07 |  | 2017-11-20 | 2017-11-21 | Dec. 15- Jan. 5, 2018 | 2018-01-18 | 2018-01-19 | 2018-01-22 |  |  |  | 3390360 | 3390360 |  | 3071299 | 3071299 |  | COA, PCCI | 2017-11-07 |  | 2017-11-20
| (January 01, 2018 - December 31, 2018) | [15 empty] | 0
| Purchase of meals | FASD | Small Value Procurement 53.9 |  | 2018-01-25 | [5 empty] | 2018-01-29 | 2018-01-29 | 2018-01-29 | 2018-01-30 | 2018-01-30 | GAA | 4000 | 4000 |  | 4000 | 4000
| Purchase of meals | FASD | Small Value Procurement 53.9 |  | 2018-01-12 | [5 empty] | 2018-01-16 | 2018-01-18 | 2018-01-18 | 2018-01-19 | 2018-01-19 | GAA | 10500 | 10500 |  | 10400 | 10400
| Purchase of meals | FASD | Small Value Procurement 53.9 |  | 2018-02-09 | [5 empty] | 2018-02-14 | 2018-02-19 | 2018-02-19 | 2018-02-19 | 2018-02-19 | GAA | 21080 | 21080 |  | 10600 | 10600
| Purchase of meals | FASD | Small Value Procurement 53.9 |  | 2018-02-06 | [5 empty] | 2018-02-08 | 2018-02-08 | 2018-02-09 | 2018-02-09 | 2018-02-09 | GAA | 9500 | 9500 |  | 9275 | 9275
| Purchase of meals | ROD | Small Value Procurement 53.10 |  | 2018-02-06 | [5 empty] | 2018-02-08 | 2018-02-09 | 2018-02-09 | 2018-02-09 | 2018-02-09 | GAA | 9800 | 9800 |  | 9050 | 9050
| Purchase of Blinds | FASD | Small Value Procurement 53.9 |  | 2017-11-16 | [5 empty] | 2018-01-10 | 2018-01-23 | 2018-01-24 | 2018-02-13 | 2018-02-13 | GAA | 164300 | 164300 |  | 147863 | 147863
| Purchase of Janitorial supplies | FASD | Shopping Ord/ Reg. Office Supplies & Eqpt. Sec 52.1b |  | 2018-02-15 | [5 empty] | 2018-03-01 | 2018-03-01 | 2018-03-01 | 2018-03-01 | 2018-03-01 | GAA | 6305 | 6305 |  | 5424.05 | 5424.05
| Purchase of Janitorial supplies | FASD | NP(Agency-Agency) |  | 2018-02-15 | [5 empty] | 2018-02-26 | 2018-02-26 | 2018-02-26 | 2018-03-01 | 2018-03-01 | GAA |  |  |  | 178.08 | 178.08
| Purchase of office supplies | FASD | NP(Agency-Agency) |  | 2018-02-15 | [5 empty] | 2018-02-26 | 2018-02-26 | 2018-02-26 | 2018-03-01 | 2018-03-01 | GAA | 78447.5 | 78447.5 |  | 4753.15 | 4753.15
| Purchase of office supplies | FASD | Shopping Ord/ Reg. Office Supplies & Eqpt. Sec 52.1b |  | 2018-02-15 | [5 empty] | 2018-03-01 | 2018-03-08 | 2018-03-09 | 2018-03-15 | 2018-03-15 |  |  |  |  | 26015 | 26015
| Purchase of office supplies | FASD | Shopping Ord/ Reg. Office Supplies & Eqpt. Sec 52.1b |  | 2018-02-15 | [5 empty] | 2018-03-01 | 2018-03-08 | 2018-03-09 | 2018-03-16 | 2018-03-16 |  |  |  |  | 24820 | 24820
| Purchase of Office supplies(Diploma Curriculum Workshop) | ROD | Shopping Ord/ Reg. Office Supplies & Eqpt. Sec 52.1b |  | 2018-03-05 | [5 empty] | 2018-03-08 | 2018-03-08 | 2018-03-08 | 2018-03-09 | 2018-03-09 | GAA | 27110 | 27110 |  | 25585 | 25585
| Printing of Registration form | FASD | Small Value Procurement 53.9 |  | 2018-02-15 | [5 empty] | 2018-02-27 | 2018-03-06 | 2018-03-07 | 2018-03-15 | 2018-03-15 | GAA | 3500 | 3500 |  | 2500 | 2500
| Purchase of office supplies | ORD | Shopping Ord/ Reg. Office Supplies & Eqpt. Sec 52.1b |  | 2018-03-01 | [5 empty] | 2018-03-09 | 2018-03-19 | 2018-03-20 | 2018-04-02 | 2018-04-02 | GAA | 48095 | 48095 |  | 7068 | 7068
| Purchase of office supplies | ROD | NP(Agency-Agency) |  | 2018-03-01 | [5 empty] | 2018-03-06 | 2018-03-06 | 2018-03-06 | 2018-04-15 | 2018-03-16 | GAA |  |  |  | 20050.5 | 20050.5
| Purchase of office supplies | ORD | Shopping Ord/ Reg. Office Supplies & Eqpt. Sec 52.1b |  | 2018-03-01 | [5 empty] | 2018-03-09 | 2018-03-19 | 2018-03-20 | 2018-04-03 | 2018-04-03 | GAA |  |  |  | 15500 | 15500
| Purchase of supplies(NSIP) |  | Shopping Ord/ Reg. Office Supplies & Eqpt. Sec 52.1b |  | 2018-03-05 | [5 empty] | 2018-03-08 | 2018-03-19 | 2018-03-19 | 2018-03-23 | 2018-04-03 | GAA | 9985 | 9985 |  | 9760 | 9760
| Purchase of office supplies | ROD | Shopping Ord/ Reg. Office Supplies & Eqpt. Sec 52.1b |  | 2018-02-27 | [5 empty] | 2018-03-12 | 2018-03-18 | 2018-03-19 | 2018-03-25 | 2018-04-02 | GAA | 85772.5 | 85772.5 |  | 30505 | 30505
| Purchase of office supplies | ROD | NP(Agency-Agency) |  | 2018-02-28 | [5 empty] | 2018-03-05 | 2018-03-06 | 2018-03-06 | 2018-03-15 | 2018-03-16 | GAA |  |  |  | 20024.34 | 20024.34
| Purchase of office supplies | ROD | Shopping Ord/ Reg. Office Supplies & Eqpt. Sec 52.1b |  | 2018-02-27 | [5 empty] | 2018-03-12 | 2018-03-18 | 2018-03-19 | 2018-03-25 | 2018-04-02 | GAA |  |  |  | 28647 | 28647
| Purchase of office supplies | ROD | Shopping Ord/ Reg. Office Supplies & Eqpt. Sec 52.1b |  | 2018-02-06 | [5 empty] | 2018-03-08 | 2018-03-18 | 2018-03-19 | 2018-04-03 | 2018-04-03 | GAA | 1840 | 1840 |  | 1452 | 1452
| Purchase of supplies (Training) | FASD | Shopping Ord/ Reg. Office Supplies & Eqpt. Sec 52.1b |  | 2018-05-25 | [5 empty] | 2018-05-28 | 2018-05-28 | 2018-05-29 | 2018-05-29 | 2018-05-29 | GAA | 5073 | 5073 |  | 4998 | 4998
| Purchase of supplies (Training) | ROD | Shopping Ord/ Reg. Office Supplies & Eqpt. Sec 52.1b |  | 2018-05-03 | [5 empty] | 2018-05-08 | 2018-05-08 | 2018-05-09 | 2018-05-09 | 2018-05-09 | GAA | 17380 | 17380 |  | 14390 | 14390
| Purchase of office supplies | ROD | NP(Agency-Agency) |  | 2018-05-08 | [5 empty] | 2018-05-11 | 2018-05-21 | 2018-05-21 | 2018-05-24 | 2018-05-24 | GAA | 93531.5 | 93531.5 |  | 46231.23 | 46231.23
| Purchase of office supplies | ROD | Shopping Ord/ Reg. Office Supplies & Eqpt. Sec 52.1b |  | 2018-05-08 | [5 empty] | 2018-06-06 | 2018-06-19 | 2018-06-20 | 2018-06-20 | 2018-06-22 | GAA |  |  |  | 5426 | 5426
| Purchase of office supplies | COA | NP(Agency-Agency) |  | 2018-04-16 | [5 empty] | 2018-04-17 | 2018-04-19 | 2018-04-23 | 2018-04-23 | 2018-04-23 | GAA | 26810 | 26810 |  | 21348.12 | 21348.12
| Purchase of office supplies | COA | Shopping Ord/ Reg. Office Supplies & Eqpt. Sec 52.1b |  | 2018-04-16 | [5 empty] | 2018-04-19 | 2018-04-25 | 2018-04-25 | 2018-05-24 | 2018-05-24 | GAA |  |  |  | 3453 | 3453
| Purchase of meals (IQA) | ROD | Small Value Procurement 53.9 |  | 2018-06-24 | [5 empty] | 2018-06-19 | 2018-06-21 | 2018-06-21 | 2018-06-25 | 2018-06-25 | GAA | 10200 | 10200 |  | 9850 | 9850
| Purchase of office supplies | FASD | Shopping Ord/ Reg. Office Supplies & Eqpt. Sec 52.1b |  | 2018-05-18 | [5 empty] | 2018-05-25 | 2018-05-05 | 2018-06-08 | 2018-06-08 | 2018-06-08 | GAA | 83975 | 83975 |  | 14450 | 14450
| Purchase of office supplies | FASD | NP(Agency-Agency) |  | 2018-05-18 | [5 empty] | 2018-05-25 | 2018-06-05 | 2018-06-06 | 2018-06-06 | 2018-06-07 | GAA |  |  |  | 11272.62 | 11272.62
| Provision of professional Services( enhancement of TESDA-CAR Website) | ROD | Small Value Procurement 53.9 |  | 2018-01-21 | [5 empty] | 2018-03-07 | 2018-03-07 | 2018-03-07 | 2018-03-08 | 2018-03-08 | GAA | 65000 | 65000 |  | 50000 | 50000
| Purchase of meals | FASD | Small Value Procurement 53.10 |  | 2018-02-19 | [5 empty] | 2018-03-07 | 2018-03-07 | 2018-03-07 | 2018-03-08 | 2018-03-08 | GAA | 358180 | 358180 |  | 36190 | 36190
| Purchase of meals | FASD | Small Value Procurement 53.11 |  | 2018-02-20 | [5 empty] | 2018-03-07 | 2018-03-07 | 2018-03-07 | 2018-03-08 | 2018-03-08 | GAA |  |  |  | 162380 | 162380
| Provision of accommodation | FASD | Lease of Real Property & Venue |  | 2018-02-19 | [5 empty] | 2018-03-07 | 2018-03-07 | 2018-03-07 | 2018-03-08 | 2018-03-08 | GAA |  |  |  | 52000 | 52000
| Purchase of meals & accommodation | FASD | Lease of Real Property & Venue |  | 2018-02-19 | [5 empty] | 2018-03-12 | 2018-03-12 | 2018-03-12 | 2018-03-13 | 2018-03-13 | GAA | 272500 | 272500 |  | 174385 | 174385
| Purchase of Toner | FASD | Shopping Ord/ Reg. Office Supplies & Eqpt. Sec 52.1b |  | 2018-03-13 | [5 empty] | 2018-03-14 | 2018-03-14 | 2018-03-14 | 2018-03-14 | 2018-03-16 | GAA | 6800 | 6800 |  | 6800 | 6800
| Tarpaulin printing | FASD | Small Value Procurement 53.9 |  | 2018-03-06 | [5 empty] | 2018-03-08 | 2018-03-09 | 2018-03-09 | 2018-03-12 | 2018-03-13 | GAA | 2650 | 2650 |  | 2350 | 2350
| Purchase of office supplies | COA | NP(Agency-Agency) |  | 2018-02-26 | [5 empty] | 2018-03-01 | 2018-03-01 | 2018-03-02 | 2018-03-06 | 2018-03-07 | GAA | 25700 | 25700 |  | 9897 | 9897
| Purchase of office supplies | COA | NP(Agency-Agency) |  | 2018-02-26 | [5 empty] | 2018-03-07 | 2018-04-09 | 2018-04-09 | 2018-04-09 | 2018-04-17 | GAA |  |  |  | 16442 | 16442
| Tarpaulin printing | ROD | Small Value Procurement 53.9 |  | 2018-02-19 | [5 empty] | 2018-02-20 | 2018-02-20 | 2018-02-20 | 2018-02-21 | 2018-02-21 | GAA | 33680 | 33680 |  | 6750 | 6750
| Purchase of meals | ROD | Small Value Procurement 53.10 |  | 2018-03-01 | [5 empty] | 2018-03-05 | 2018-03-05 | 2018-03-06 | 2018-03-08 | 2018-03-08 | GAA | 3750 | 3750 |  | 3750 | 3750
| Purchase of meals | ROD | Small Value Procurement 53.10 |  | 2018-03-19 | [5 empty] | 2018-03-22 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | GAA | 19800 | 19800 |  | 17600 | 17600
| Provision of meals & accommodation | ROD | Lease of Real Property & Venue |  | 2018-03-12 | [5 empty] | 2018-03-19 | 2018-03-20 | 2018-03-20 | 2018-03-21 | 2018-03-21 | GAA | 89300 | 89300 |  | 88100 | 88100
| Purchase of office supplies | ROD | Shopping Ord/ Reg. Office Supplies & Eqpt. Sec 52.1b |  | 2018-03-05 | [5 empty] | 2018-03-08 | 2018-03-19 | 2018-03-20 | 2018-03-23 | 2018-03-23 | GAA | 1840 | 1840 |  | 1452 | 1452
| Provision of accommodation | FASD | Small Value Procurement 53.9 |  | 2018-03-27 | [5 empty] | 2018-04-03 | 2018-04-03 | 2018-04-03 | 2018-04-04 | 2018-04-04 | GAA | 22000 | 22000 |  | 20391 | 20391
| Purchase of meals | ROD | Small Value Procurement 53.10 |  | 2018-04-10 | [5 empty] | 2018-04-13 | 2018-04-16 | 2018-04-16 | 2018-04-18 | 2018-04-18 | GAA | 11620 | 11620 |  | 11282 | 11282
| Purchase of plumbing supplies | FASD | Small Value Procurement 53.9 |  | 2018-04-23 | [5 empty] | 2018-04-27 | 2018-05-03 | 2018-05-03 | 2018-05-03 | 2018-05-03 | GAA | 18800 | 18800 |  | 7167 | 7167
| Installation Services | FASD | Small Value Procurement 53.9 |  | 2018-04-23 | [5 empty] | 2018-05-03 | 2018-05-03 | 2018-05-15 | 2018-05-15 | 2018-05-15 | GAA |  |  |  | 9500 | 9500
| Purchase of meals | ROD | Small Value Procurement 53.9 |  | 2018-04-12 | [5 empty] | 2018-04-16 | 2018-04-16 | 2018-04-16 | 2018-04-22 | 2018-04-22 | GAA | 87720 | 87720 |  | 45300 | 45300
| Provision of accommodation | ROD | Lease of Real Property & Venue |  | 2018-04-12 | [5 empty] | 2018-04-16 | 2018-04-16 | 2018-04-16 | 2018-04-19 | 2018-04-22 | GAA |  |  |  | 39600 | 39600
| Purchase of meals | ROD | Small Value Procurement 53.9 |  | 2018-04-18 | [5 empty] | 2018-04-24 | 2018-04-25 | 2018-04-25 | 2018-04-27 | 2018-04-27 | GAA | 20040 | 20040 |  | 14250 | 14250
| Purchase of meals | FASD | Small Value Procurement 53.9 |  | 2018-04-12 | [5 empty] | 2018-04-25 | 2018-04-26 | 2018-04-27 | 2018-05-02 | 2018-05-27 | GAA | 14400 | 14400 |  | 13600 | 13600
| Purchase of meals | ROD | Small Value Procurement 53.9 |  | 2018-04-26 | [5 empty] | 2018-05-03 | 2018-05-03 | 2018-05-03 | 2018-05-04 | 2018-05-04 | GAA | 7100 | 7100 |  | 6525 | 6525
| Purchase of training supplies | ROD | Shopping Ord/ Reg. Office Supplies & Eqpt. Sec 52.1b |  | 2018-05-03 | [5 empty] | 2018-05-08 | 2018-05-09 | 2018-05-09 | 2018-05-09 | 2018-05-09 | GAA | 17380 | 17380 |  | 14390 | 14390
| Purchase of meals | FASD | Small Value Procurement 53.10 |  | 2018-03-28 | [5 empty] | 2018-04-03 | 2018-04-03 | 2018-04-04 | 2018-04-05 | 2018-04-05 | GAA | 43140 | 43140 |  | 22440 | 22440
| Purchase of meals | ROD | Small Value Procurement 53.11 |  | 2018-02-12 | [5 empty] | 2018-03-12 | 2018-03-13 | 2018-03-13 | 2018-03-13 | 2018-03-13 | GAA | 22500 | 22500 |  | 17500 | 17500
| Purchase of office supplies | ROD | NP(Agency-Agency) |  | 2018-05-10 | [5 empty] | 2018-05-10 | 2018-05-11 | 2018-05-11 | 2018-05-24 | 2018-05-24 | GAA | 15450 | 15450 |  | 15450 | 15450
| Labor for removal of septic tank solid waste | FASD | Small Value Procurement 53.10 |  | 2018-04-23 | [5 empty] | 2018-05-03 | 2018-05-10 | 2018-05-10 | 2018-05-16 | 2018-05-16 | GAA | 45000 | 45000 |  | 42000 | 42000
| Provision of accommodation | FASD | Lease of Real Property & Venue |  | 2018-04-18 | [5 empty] | 2018-05-02 | 2018-05-03 | 2018-05-03 | 2018-05-11 | 2018-05-11 | GAA | 278000 | 278000 |  | 11000 | 11000
| Purchase of meals | FASD | Small Value Procurement 53.11 |  | 2018-04-18 | [5 empty] | 2018-05-02 | 2018-05-02 | 2018-05-03 | 2018-05-11 | 2018-05-11 | GAA |  |  |  | 207250 | 207250
| Provision of meals and accommodation | FASD | Small Value Procurement 53.11 |  | 2018-05-21 | [5 empty] | 2018-05-30 | 2018-05-30 | 2018-05-30 | 2018-06-01 | 2018-06-01 | GAA | 124800 | 124800 |  | 123000 | 123000
| Provision of Transportation services | FASD | Lease of Real Property & Venue |  | 2018-05-17 | [5 empty] | 2018-05-23 | 2018-05-28 | 2018-05-28 | 2018-06-04 | 2018-06-04 | GAA | 26000 | 26000 |  | 22000 | 22000
| Purchase of meals | ROD | Small Value Procurement 53.10 |  | 2018-05-18 | [5 empty] | 2018-05-22 | 2018-05-22 | 2018-05-23 | 2018-05-25 | 2018-05-25 | GAA | 23040 | 23040 |  | 21920 | 21920
| Purchase of meals | FASD | Small Value Procurement 53.10 |  | 2018-05-11 | [5 empty] | 2018-05-21 | 2018-05-21 | 2018-05-22 | 2018-05-22 | 2018-05-22 | GAA | 16380 | 16380 |  | 16038 | 16038
| Provision of Transportation services | FASD | Lease of Real Property & Venue |  | 2018-04-20 | [5 empty] | 2018-05-03 | 2018-05-03 | 2018-05-03 | 2018-05-11 | 2018-05-11 | GAA | 35000 | 35000 |  | 28000 | 28000
| Purchase of meals | ROD | Small Value Procurement 53.10 |  | 2018-05-21 | [5 empty] | 2018-05-31 | 2018-05-31 | 2018-06-06 | 2018-06-07 | 2018-06-07 | GAA | 52000 | 52000 |  | 45200 | 45200
| Provision of meals and accommodation | ROD | Lease of Real Property & Venue |  | 2018-06-08 | [5 empty] | 2018-06-17 | 2018-06-18 | 2018-06-19 | 2018-06-20 | 2018-06-20 | GAA | 79500 | 79500 |  | 71400 | 71400
| Purchase of office supplies | ORD | NP(Agency-Agency) |  | 2018-05-26 | [5 empty] | 2018-06-07 | 2018-06-19 | 2018-06-26 | 2018-06-27 | 2018-06-27 | GAA | 41345 | 41345 |  | 5031.04 | 5031.04
| Provision of accommodation | ROD | Lease of Real Property & Venue |  | 2018-05-11 | [5 empty] | 2018-05-11 | 2018-05-15 | 2018-05-15 | 2018-05-16 | 2018-05-16 | GAA | 17600 | 17600 |  | 9000 | 9000
| Purchase of office supplies | FASD | Shopping Ord/ Reg. Office Supplies & Eqpt. Sec 52.1b |  | 2018-05-11 | [5 empty] | 2018-06-05 | 2018-06-08 | 2018-06-08 | 2018-06-13 | 2018-06-13 | GAA | 83975 | 83975 |  | 14450 | 14450
| Purchase of office supplies | FASD | Shopping Ord/ Reg. Office Supplies & Eqpt. Sec 52.1b |  | 2018-05-11 | [5 empty] | 2018-06-05 | 2018-06-08 | 2018-06-08 | 2018-06-15 | 2018-06-19 |  |  |  |  | 35340 | 35340
| Purchase of office supplies | ROD | Shopping Ord/ Reg. Office Supplies & Eqpt. Sec 52.1b |  | 2018-05-08 | [5 empty] | 2018-06-06 | 2018-06-20 | 2018-06-20 | 2018-06-20 | 2018-06-22 | GAA | 93531.5 | 93531.5 |  | 5426 | 5426
| Purchase of meals | ROD | Small Value Procurement 53.10 |  | 2018-06-08 | [5 empty] | 2018-06-18 | 2018-06-19 | 2018-06-19 | 2018-06-20 | 2018-06-20 | GAA | 7500 | 7500 |  | 7500 | 7500
| Purchase of meals | FASD | Small Value Procurement 53.9 |  | 2018-06-18 | [5 empty] | 2018-06-27 | 2018-06-28 | 2018-06-28 | 2018-06-30 | 2018-06-30 | GAA | 246000 | 246000 |  | 238500 | 238500
| Purchase of meals | ROD | Small Value Procurement 53.10 |  | 2018-06-14 | [5 empty] | 2018-06-19 | 2018-06-21 | 2018-06-21 | 2018-06-25 | 2018-06-25 | GAA | 10200 | 10200 |  | 9850 | 9850
| Purchase of meals | ROD | Small Value Procurement 53.10 |  | 2018-06-05 | [5 empty] | 2018-06-08 | 2018-06-09 | 2018-06-09 | 2018-06-11 | 2018-06-11 | GAA | 10200 | 10200 |  | 9580 | 9580
| Purchase of meals | FASD | Small Value Procurement 53.10 |  | 2018-06-13 | [5 empty] | 2018-06-19 | 2018-06-21 | 2018-06-21 | 2018-06-21 | 2018-06-21 | GAA | 9350 | 9350 |  | 8850 | 8850
| Purchase of meals | FASD | Small Value Procurement 53.10 |  | 2018-05-03 | [5 empty] | 2018-05-10 | 2018-05-10 | 2018-05-10 | 2018-05-11 | 2018-05-11 | GAA | 8000 | 8000 |  | 7700 | 7700
| Purchase of office supplies | FASD | Shopping Ord/ Reg. Office Supplies & Eqpt. Sec 52.1b |  | 2018-06-18 | [5 empty] | 2018-06-20 | 2018-06-21 | 2018-06-21 | 2018-06-21 | 2018-06-21 | GAA | 25825 | 25825 |  | 25825 | 25825
| Purchase of National Certificates (NC) | FASD | NP(Agency-Agency) |  | 2018-04-03 | [5 empty] | 2018-04-03 | 2018-04-04 | 2018-04-10 | 2018-04-10 | 2018-04-10 | SSP | 70000 | 70000 |  | 70000 | 70000
Total Alloted Budget of Procurement Activities | [16 empty] | 6570161 |  |  | 5516539.13
Total Contract Price of Procurement Actitvites Conducted | [16 empty] | 5516539.13
Total Savings (Total Alloted Budget - Total Contract Price) | [16 empty] | 1053621.87
0N-GOING PROCUREMENT ACTIVITIES
Total Alloted Budget of On-going Procurement Activities
| Prepared by: | [7 empty] | Recommended for Approval by: | [10 empty] | APPROVED:

## 2nd
ANNEX B |  | ANNEX A
|  | Department of Budget and Management Annual Procurement Plan for FY 2006 | [18 empty] | Technical Education and Skills Development Authority
Cordillera Administrative Region
Procurement Monitoring Report as of December 2018
Code (UACS/PAP) | Procurement Program/Project | PMO/ End-User | Mode of Procurement | Schedule for Each Procurement Activity | [11 empty] | Source of Funds | ABC (PhP) |  |  | Remarks (brief description of Program/Project) | PMO/ End-User | Mode of Procurement | Actual Procurement Activity | [11 empty] | Source of Funds | ABC (PhP) |  |  | Contract Cost (PhP) |  |  | List of Invited Observers | Date of Receipt of Invitation | [5 empty] | Remarks (Explaining changes from the APP)
|  |  |  | Pre-Proc Conference | Ads/Post of IAEB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Contract Award | Contract Signing | Notice to Proceed | Delivery/ Accept | Payment Process |  | Total | MOOE | CO |  |  |  | Pre-Proc Conference | Ads/Post of IB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Notice of Award | Contract Signing | Notice to Proceed | Delivery/ Completion | Inspection & Acceptance |  | Total | MOOE | CO | Total | MOOE | CO |  | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Delivery/ Completion/ Acceptance (If applicable)
COMPLETED PROCUREMENT ACTIVITIES
[36 empty] | 0 |  |  | 0
| Purchase of office supplies | [19 empty] | FASD | NP(Agency-Agency) |  | 2018-08-01 | [5 empty] | 2018-08-08 | 2018-08-08 | 2018-08-13 | 2018-08-15 | 2018-08-15 | GAA | 90457.5 | 90457.5 |  | 25338.6 | 25338.6
| Purchase of office supplies | [19 empty] | ROD | NP(Agency-Agency) |  | 2018-05-08 | [5 empty] | 2018-06-06 | 2018-06-21 | 2018-06-22 | 2018-07-02 | 2018-07-04 | GAA | 95531.5 | 95531.5 |  | 33050 | 33050
| Hotel accommodation (TESDA-CO Rep.) | [19 empty] | ROD | Lease of Real Property & Venue |  | 2018-06-15 | [5 empty] | 2018-06-19 | 2018-06-19 | 2018-06-20 | 2018-06-27 | 2018-06-27 | GAA | 9200 | 9200 |  | 6760 | 6760
| Purchase of meals | [19 empty] | ROD | Small Value Procurement 53.9 |  | 2018-07-03 | [5 empty] | 2018-07-09 | 2018-07-09 | 2018-07-09 | 2018-07-10 | 2018-07-10 | GAA | 16250 | 16250 |  | 15625 | 15625
| Purchase of meals | [19 empty] | ROD | Small Value Procurement 53.10 |  | 2018-07-02 | [5 empty] | 2018-07-04 | 2018-07-05 | 2018-07-06 | 2018-07-06 | 2018-07-06 | GAA | 10200 | 10200 |  | 9675 | 9675
| Purchase of meals | [19 empty] | FASD | Small Value Procurement 53.10 |  | 2018-08-15 | [5 empty] | 2018-08-20 | 2018-08-20 | 2018-08-22 | 2018-08-24 | 2018-08-24 | GAA | 127950 | 127950 |  | 77000 | 77000
| Purchase of office supplies | [19 empty] | ROD | Shopping Ord/ Reg. Office Supplies & Eqpt. Sec 52.1b |  | 2018-06-06 | [5 empty] | 2018-06-11 | 2018-06-28 | 2018-06-28 | 2018-07-02 | 2018-07-04 | GAA | 9680 | 9680 |  | 9520 | 9520
| Purchase of National Certificates (NC) | [19 empty] | FASD | NP(Agency-Agency) |  | 2018-06-22 | [5 empty] | 2018-06-22 | 2018-06-22 | 2018-06-22 | 2018-07-10 | 2018-07-10 | SSP | 280000 | 280000 |  | 280000 | 280000
| Purchase of National Certificates (NC) | [19 empty] | FASD | NP(Agency-Agency) |  | 2018-09-20 | [5 empty] | 2018-09-20 | 2018-09-20 | 2018-09-20 | 2018-09-25 | 2018-09-25 | SSP | 280000 | 280000 |  | 280000 | 280000
| Purchase of meals | [19 empty] | FASD | Small Value Procurement 53.10 |  | 2018-09-14 | [5 empty] | 2018-09-20 | 2018-09-20 | 2018-09-20 | 2018-09-24 | 2018-09-24 | GAA | 14000 | 14000 |  | 13550 | 13550
| Printing of tarpaulin | [19 empty] | FASD | Small Value Procurement 53.9 |  | 2018-07-02 | [5 empty] | 2018-07-06 | 2018-07-09 | 2018-07-09 | 2018-07-11 | 2018-09-24 | GAA | 2010 | 2010 |  | 1880 | 1880
| Purchase of office supplies | [19 empty] | FASD | NP(Agency-Agency) |  | 2018-07-13 | [5 empty] | 2018-07-18 | 2018-07-10 | 2018-07-10 | 2018-08-15 | 2018-08-15 | GAA | 10500 | 10500 |  | 10500 | 10500
| Purchase of office supplies | [19 empty] | ROD | Shopping Ord/ Reg. Office Supplies & Eqpt. Sec 52.1b |  | 2018-08-03 | [5 empty] | 2018-08-08 | 2018-08-13 | 2018-08-13 | 2018-08-15 | 2018-08-15 | GAA | 5500 | 5500 |  | 4550 | 4550
| Purchase of office supplies | [19 empty] | FASD | Shopping Ord/ Reg. Office Supplies & Eqpt. Sec 52.1b |  | 2018-06-14 | [5 empty] | 2018-07-30 | 2018-08-22 | 2018-08-24 | 2018-08-30 | 2018-08-31 | GAA | 94147.5 | 94147.5 |  | 42005 | 42005
| Purchase of office supplies | [19 empty] | FASD | Shopping Ord/ Reg. Office Supplies & Eqpt. Sec 52.1b |  | 2018-06-14 | [5 empty] | 2018-07-30 | 2018-08-03 | 2018-08-24 | 2018-09-24 | 2018-09-24 | GAA |  |  |  | 6725 | 6725
| Purchase of Janitorial supplies | [19 empty] | FASD | Shopping Ord/ Reg. Office Supplies & Eqpt. Sec 52.1b |  | 2018-06-25 | [5 empty] | 2018-07-05 | 2018-07-19 | 2018-07-19 | 2018-07-20 | 2018-07-20 | GAA | 9225 | 9225 |  | 5036.78 | 5036.78
| Purchase of Office furniture | [19 empty] | FASD | Small Value Procurement 53.9 |  | 2018-06-25 | [5 empty] | 2018-06-28 | 2018-07-13 | 2018-07-19 | 2018-08-01 | 2018-08-06 | GAA | 909050 | 909050 |  | 872200 | 872200
| Purchase of IT accessories | [19 empty] | FASD | Small Value Procurement 53.9 |  | 2018-06-22 | [5 empty] | 2018-07-04 | 2018-07-09 | 2018-07-09 | 2018-07-11 | 2018-07-11 | GAA | 1000 | 1000 |  | 1000 | 1000
| Purchase of meals | [19 empty] | ROD | Small Value Procurement 53.9 |  | 2018-06-21 | [5 empty] | 2018-06-26 | 2018-06-26 | 2018-06-26 | 2018-06-28 | 2018-06-28 | GAA | 8800 | 8800 |  | 8500 | 8500
| Purchase of meals | [19 empty] | ROD | Small Value Procurement 53.10 |  | 2018-08-03 | [5 empty] | 2018-08-09 | 2018-08-09 | 2018-08-10 | 2018-08-10 | 2018-08-10 | GAA | 9000 | 9000 |  | 8550 | 8550
| Purchase of meals | [19 empty] | ROD | Small Value Procurement 53.10 |  | 2018-08-14 | [5 empty] | 2018-08-17 | 2018-08-17 | 2018-08-20 | 2018-08-20 | 2018-08-20 | GAA | 6095 | 6095 |  | 5865 | 5865
| Tarpaulin printing | [19 empty] | ROD | Small Value Procurement 53.9 |  | 2018-07-02 | [5 empty] | 2018-07-09 | 2018-07-09 | 2018-07-09 | 2018-07-11 | 2018-07-13 | GAA | 2010 | 2010 |  | 1880 | 1880
| Purchase of meals | [19 empty] | ROD | Small Value Procurement 53.10 |  | 2018-07-23 | [5 empty] | 2018-07-27 | 2018-07-27 | 2018-08-01 | 2018-08-01 | 2018-08-01 | GAA | 28800 | 28800 |  | 26650 | 26650
| Purchase of meals | [19 empty] | FASD | Small Value Procurement 53.10 |  | 2018-07-24 | [5 empty] | 2018-07-30 | 2018-07-31 | 2018-08-01 | 2018-08-02 | 2018-08-02 | GAA | 18800 | 18800 |  | 17300 | 17300
| Printing of tarpaulin | [19 empty] | FASD | Small Value Procurement 53.9 |  | 2018-08-15 | [5 empty] | 2018-08-21 | 2018-08-22 | 2018-08-22 | 2018-08-23 | 2018-08-23 | GAA | 61600 | 61600 |  | 23500 | 23500
| Printing of tarpaulin | [19 empty] | FASD | Small Value Procurement 53.10 |  | 2018-08-07 | [5 empty] | 2018-08-10 | 2018-08-16 | 2018-08-16 | 2018-08-17 | 2018-08-17 | GAA | 34360 | 34360 |  | 2160 | 2160
| Purchase of Electrical Supplies | [19 empty] | FASD | Small Value Procurement 53.10 |  | 2018-07-17 | [5 empty] | 2018-07-25 | 2018-07-30 | 2018-07-31 | 2018-08-23 | 2018-08-23 | GAA | 22615 | 22615 |  | 4880 | 4880
| Purchase of Electrical Supplies | [19 empty] | FASD | Small Value Procurement 53.11 |  | 2018-07-18 | [5 empty] | 2018-07-25 | 2018-07-30 | 2018-07-31 | 2018-08-01 | 2018-08-03 | GAA |  |  |  | 10361 | 10361
| Purchase of Automotive Supplies (Tires) | [19 empty] | FASD | Small Value Procurement 53.10 |  | 2018-07-30 | [5 empty] | 2018-07-25 | 2018-07-30 | 2018-07-31 | 2018-08-27 | 2018-08-23 | GAA | 24800 | 24800 |  | 24600 | 24600
| Purchase of Automotive Supplies | [19 empty] | FASD | Small Value Procurement 53.10 |  | 2018-07-30 | [5 empty] | 2018-11-09 | 2018-11-09 | 2018-11-20 | 2018-11-20 | 2018-11-22 |  | 7700 | 7700 |  | 7632 | 7632
| Purchase of office supplies | [19 empty] | FASD | Shopping Ord/ Reg. Office Supplies & Eqpt. Sec 52.1b |  | 2018-08-03 | [5 empty] | 2018-08-29 | 2018-09-10 | 2018-09-10 | 2018-09-17 | 2018-09-18 | GAA | 49904 | 49904 |  | 12690 | 12690
| Purchase of office supplies | [19 empty] | FASD | Shopping Ord/ Reg. Office Supplies & Eqpt. Sec 52.1b |  | 2018-08-03 | [5 empty] | 2018-08-29 | 2018-09-10 | 2018-09-10 | 2018-09-14 | 2018-09-14 | GAA |  |  |  | 35100 | 35100
| Purchase of office supplies | [19 empty] | ORD | NP(Agency-Agency) |  | 2018-08-03 | [5 empty] | 2018-08-13 | 2018-08-20 | 2018-08-20 | 2018-08-20 | 2018-08-23 | GAA |  |  |  | 865.47 | 865.47
| Printing of STICKERS | [19 empty] | FASD | Small Value Procurement 53.9 |  | 2018-08-17 | [5 empty] | 2018-08-22 | 2018-08-22 | 2018-08-22 | 2018-08-24 | 2018-08-24 | GAA | 42000 | 42000 |  | 39000 | 39000
| Purchase of T-shirts | [19 empty] | FASD | Small Value Procurement 53.9 |  | 2018-08-07 | [5 empty] | 2018-08-10 | 2018-08-22 | 2018-08-22 | 2018-08-24 | 2018-08-24 | GAA | 34000 | 34000 |  | 32200 | 32200
| Purchase of meals | [19 empty] | FASD | Small Value Procurement 53.9 |  | 2018-09-07 | [5 empty] | 2018-09-11 | 2018-09-10 | 2018-09-11 | 2018-09-11 | 2018-09-11 | GAA | 25650 | 25650 |  | 23400 | 23400
| Purchase of Plaques | [19 empty] | FASD | Small Value Procurement 53.10 |  | 2018-08-29 | [5 empty] | 2018-09-06 | 2018-09-08 | 2018-09-08 | 2018-09-10 | 2018-09-10 | GAA | 49000 | 49000 |  | 31350 | 31350
| Publication services | [19 empty] | ROD | Small Value Procurement 53.9 |  | 2018-07-22 | [5 empty] | 2018-08-08 | 2018-08-29 | 2018-08-29 | 2018-09-03 | 2018-09-03 | GAA | 22000 | 22000 |  | 18842 | 18842
| Purchase of electrical supplies | [19 empty] | FASD | Small Value Procurement 53.9 |  | 2018-07-17 | [5 empty] | 2018-07-25 | 2018-07-31 | 2018-07-31 | 2018-08-01 | 2018-08-03 | GAA | 22615 | 22615 |  | 10361 | 10361
| Publication services | [19 empty] | FASD | Small Value Procurement 53.9 |  | 2018-07-30 | [5 empty] | 2018-08-08 | 2018-08-29 | 2018-08-29 | 2018-09-03 | 2018-09-03 | GAA | 22000 | 22000 |  | 18842 | 18842
| Purchase of meals | [19 empty] | FASD | Small Value Procurement 53.10 |  | 2018-08-16 | [5 empty] | 2018-08-22 | 2018-08-22 | 2018-08-22 | 2018-08-23 | 2018-08-23 | GAA | 8700 | 8700 |  | 8100 | 8100
| Purchase of office supplies | [19 empty] | ROD | Shopping Ord/ Reg. Office Supplies & Eqpt. Sec 52.1b |  | 2018-08-03 | [5 empty] | 2018-10-15 | 2018-10-19 | 2018-10-19 | 2018-10-22 | 2018-10-22 | GAA | 68414 | 68414 |  | 19260 | 19260
| Purchase of meals | [19 empty] | FASD | Small Value Procurement 53.10 |  | 2018-09-27 | [5 empty] | 2018-10-01 | 2018-10-01 | 2018-10-01 | 2018-10-02 | 2018-10-02 | GAA | 3300 | 3300 |  | 3150 | 3150
| Purchase of office supplies | [19 empty] | ROD | Shopping Ord/ Reg. Office Supplies & Eqpt. Sec 52.1b |  | 2018-09-21 | [5 empty] | 2018-10-29 | 2018-11-20 | 2018-11-20 | 2018-12-05 | 2018-12-05 | GAA | 5650 | 5650 |  | 4800 | 4800
| Purchase of office supplies | [19 empty] | ROD | Shopping Ord/ Reg. Office Supplies & Eqpt. Sec 52.1b |  | 2018-07-30 | [5 empty] | 2018-08-09 | 2018-08-15 | 2018-08-16 | 2018-08-17 | 2018-08-17 | GAA | 77684 | 77684 |  | 44906 | 44906
| Purchase of office supplies | [19 empty] | ROD | NP(Agency-Agency) |  | 2018-07-31 | [5 empty] | 2018-08-07 | 2018-08-15 | 2018-08-16 | 2018-08-20 | 2018-08-23 | GAA |  |  |  | 23871.34 | 23871.34
| Printing of Newsletter | [19 empty] | ROD | Shopping Ord/ Reg. Office Supplies & Eqpt. Sec 52.1b |  | 2018-11-22 | [5 empty] | 2018-12-12 | 2018-12-12 | 2018-12-13 | 2018-12-27 | 2018-12-27 | GAA | 11875 | 11875 |  | 11800 | 11800
| Publication services | [19 empty] | FASD | Small Value Procurement 53.9 |  | 2018-10-04 | [5 empty] | 2018-10-08 | 2018-10-09 | 2018-10-09 | 2018-10-14 | 2018-10-14 | GAA | 6000 | 6000 |  | 5888 | 5888
| Purchase of meals | [19 empty] | FASD | Small Value Procurement 53.10 |  | 2018-10-01 | [5 empty] | 2018-10-02 | 2018-10-02 | 2018-10-02 | 2018-10-05 | 2018-10-05 | GAA | 11700 | 11700 |  | 11050 | 11050
| Purchase of office supplies | [19 empty] | ORD | NP(Agency-Agency) |  | 2018-11-07 | [5 empty] | 2018-11-09 | 2018-11-10 | 2018-11-10 | 2018-11-14 | 2018-11-15 | GAA | 49860 | 49860 |  | 22869.01 | 22869.01
| Purchase of office supplies | [19 empty] | ORD | Shopping Ord/ Reg. Office Supplies & Eqpt. Sec 52.1b |  | 2018-11-07 | [5 empty] | 2018-11-16 | 2018-11-22 | 2018-11-22 | 2018-11-22 | 2018-12-04 | GAA |  |  |  | 20468 | 20468
| Purchase of office supplies | [19 empty] | ORD | Shopping Ord/ Reg. Office Supplies & Eqpt. Sec 52.1b |  | 2018-11-07 | [5 empty] | 2018-11-16 | 2018-11-22 | 2018-11-22 | 2018-11-28 | 2018-11-28 | GAA |  |  |  | 4956 | 4956
| Tarpaulin printing | [19 empty] | ROD | Small Value Procurement 53.9 |  | 2018-10-01 | [5 empty] | 2018-10-10 | 2018-10-10 | 2018-10-10 | 2018-10-12 | 2018-10-12 | GAA | 2400 | 2400 |  | 1050 | 1050
| Purchase of Automotive Supplies | [19 empty] | FASD | Small Value Procurement 53.9 |  | 2018-11-05 | [5 empty] | 2018-11-14 | 2018-11-20 | 2018-11-21 | 2018-11-22 | 2018-11-22 | GAA | 7700 | 7700 |  | 7632 | 7632
| Purchase of office supplies | [19 empty] | FASD | Small Value Procurement 53.9 | [7 empty] | 2018-11-23 | 2018-12-04 | 2018-12-04 | 2018-12-13 | 2018-12-13 | GAA | 13600 | 13600 |  | 7745 | 7745
| Purchase of Electrical Supplies | [19 empty] | FASD | Small Value Procurement 53.9 |  | 2018-11-20 | [5 empty] | 2018-12-12 | 2018-12-13 | 2018-12-13 | 2018-12-17 | 2018-12-18 | GAA | 6600 | 6600 |  | 6400 | 6400
| Purchase of Automotive Supplies | [19 empty] | FASD | Small Value Procurement 53.9 |  | 2018-11-08 | [5 empty] | 2018-11-14 | 2018-11-20 | 2018-11-20 | 2018-11-22 | 2018-11-22 | GAA | 3410 | 3410 |  | 3410 | 3410
| Hotel accommodation (TESDA-CO Audit team Rep.) | [19 empty] | ROD | Lease of Real Property & Venue |  | 2018-11-12 | [5 empty] | 2018-11-15 | 2018-11-15 | 2018-11-15 | 2018-11-22 | 2018-11-23 | GAA | 16500 | 16500 |  | 12150 | 12150
| Purchase of office supplies | [19 empty] | FASD | Small Value Procurement 53.9 |  | 2018-11-14 | [5 empty] | 2018-11-15 | 2018-11-21 | 2018-11-21 | 2018-11-22 | 2018-11-23 | GAA | 17300 | 17300 |  | 17300 | 17300
| Hotel accommodation (Sensitivity Training Resource Speaker ) | [19 empty] | ROD | Lease of Real Property & Venue |  | 2018-11-20 | [5 empty] | 2018-11-23 | 2018-11-25 | 2018-11-25 | 2018-11-25 | 2018-11-27 | GAA | 7200 | 7200 |  | 7200 | 7200
| Purchase of office supplies | [19 empty] | ROD | Shopping Ord/ Reg. Office Supplies & Eqpt. Sec 52.1b |  | 2018-11-20 | [5 empty] | 2018-11-22 | 2018-11-23 | 2018-11-23 | 2018-11-24 | 2018-11-24 | GAA | 22920 | 22920 |  | 16105 | 16105
| Purchase of office supplies | [19 empty] | FASD | Shopping Ord/ Reg. Office Supplies & Eqpt. Sec 52.1b |  | 2018-09-20 | [5 empty] | 2018-10-04 | 2018-10-06 | 2018-10-06 | 2018-10-11 | 2018-10-11 | GAA | 30759 | 30759 |  | 28451.7 | 28451.7
| Purchase of office supplies | [19 empty] | ROD | Shopping Ord/ Reg. Office Supplies & Eqpt. Sec 52.1b |  | 2018-10-15 | [5 empty] | 2018-10-19 | 2018-10-19 | 2018-10-19 | 2018-10-24 | 2018-10-24 | GAA | 12770 | 12770 |  | 12700 | 12700
| Purchase of meals (CIS) | [19 empty] | FASD | Small Value Procurement 53.9 |  | 2018-11-15 | [5 empty] | 2018-11-23 | 2018-11-23 | 2018-11-23 | 2018-11-29 | 2018-11-29 | GAA | 19200 | 19200 |  | 18900 | 18900
| Purchase of T-shirts | [19 empty] | FASD | Small Value Procurement 53.9 |  | 2018-11-15 | [5 empty] | 2018-11-23 | 2018-11-23 | 2018-11-23 | 2018-11-29 | 2018-11-29 | GAA | 12650 | 12650 |  | 8640 | 8640
| Purchase of Printer | [19 empty] | FASD | Shopping Ord/ Reg. Office Supplies & Eqpt. Sec 52.1b |  | 2018-12-10 | [5 empty] | 2018-12-18 | 2018-12-19 | 2018-12-19 | 2018-12-19 | 2018-12-19 | GAA | 5000 | 5000 |  | 4000 | 4000
| Purchase of office supplies | [19 empty] | FASD | Shopping Ord/ Reg. Office Supplies & Eqpt. Sec 52.1b |  | 2018-12-12 | [5 empty] | 2018-12-18 | 2018-12-19 | 21/19/2018 | 2018-12-21 | 2018-12-19 | GAA | 49405 | 49405 |  | 8070 | 8070
| Purchase of office supplies | [19 empty] | FASD | Shopping Ord/ Reg. Office Supplies & Eqpt. Sec 52.1b |  | 2018-12-12 | [5 empty] | 2018-12-18 | 2018-12-19 | 2018-12-20 | 2018-12-21 | 2018-12-19 | GAA |  |  |  | 36066 | 36066
| Purchase of Janitorial supplies | [19 empty] | FASD | NP(Agency-Agency) |  | 2018-12-03 | [5 empty] | 2018-12-12 | 2018-12-14 | 2018-12-14 | 2018-12-21 | 2018-12-21 | GAA | 24205 | 24205 |  | 1338.252 | 1338.252
| Purchase of Janitorial supplies | [19 empty] | FASD | Shopping Ord/ Reg. Office Supplies & Eqpt. Sec 52.1b |  | 2018-12-03 | [5 empty] | 2018-12-20 | 2018-12-20 | 2018-12-21 | 2018-12-21 | 2018-12-21 | GAA |  |  |  | 18657.95 | 18657.95
| Purchase of meals | [19 empty] | FASD | Small Value Procurement 53.9 |  | 2018-12-07 | [5 empty] | 2018-12-20 | 2018-12-20 | 2018-12-21 | 2018-12-21 | 2018-12-21 | GAA | 72900 | 72900 |  | 72900 | 72900
| Purchase of office supplies | [19 empty] | FASD | NP(Agency-Agency) |  | 2018-11-19 | [5 empty] | 2018-11-27 | 2018-11-27 | 2018-12-13 | 2018-12-14 | 2018-12-14 | GAA | 82265 | 82265 |  | 16295 | 16295
| Repair and maintenance supplies | [19 empty] | FASD | Small Value Procurement 53.9 |  | 2018-12-12 | [5 empty] | 2018-12-20 | 2018-12-21 | 2018-12-21 | 2018-12-27 | 2018-12-27 | GAA | 147700 | 147700 |  | 79123 | 79123
| Purchase of IT accessories | [19 empty] | FASD | Small Value Procurement 53.9 |  | 2018-11-21 | [5 empty] | 2018-12-20 | 2018-12-21 | 2018-12-21 | 2018-12-28 | 2018-12-28 | GAA | 16500 | 16500 |  | 14513.9 | 14513.9
| Purchase of meals | [19 empty] | ROD | Small Value Procurement 53.9 |  | 2018-07-02 | [5 empty] | 2018-07-05 | 2018-07-05 | 2018-07-05 | 2018-07-05 | 2018-07-05 | GAA | 8480 | 8480 |  | 8150 | 8150
| Purchase of office supplies | [19 empty] | ORD | NP(Agency-Agency) |  | 2018-07-13 | [5 empty] | 2018-07-26 | 2018-07-26 | 2018-07-28 | 2018-07-31 | 2018-07-31 | GAA | 19030 | 19030 |  | 18240 | 18240
| Hotel meals and accommodation (Newly promugated training regulations) | [19 empty] | ROD | Lease of Real Property & Venue |  | 2018-09-12 | [5 empty] | 2018-09-28 | 2018-10-01 | 2018-10-01 | 2018-10-05 | 2018-10-05 | GAA | 482300 | 482300 |  | 433300 | 433300
0
0
Total Alloted Budget of Procurement Activities | [35 empty] | 3780427.5 |  |  | 3098400.002
Total Contract Price of Procurement Actitvites Conducted | [35 empty] | 3098400.002
Total Savings (Total Alloted Budget - Total Contract Price) | [35 empty] | 682027.498
0N-GOING PROCUREMENT ACTIVITIES
Total Alloted Budget of On-going Procurement Activities
[21 empty] | Prepared by: | [8 empty] | Recommended for Approval by: | [9 empty] | APPROVED: